## Sprint Plan
Day | Sprint | Task # | Layer | Task | Description | Est. Hours
Day 1 | Setup - Infra | 1 | Infra | Init Next.js repo | bunx create-next-app for the frontend/API app. Set up folder structure and TypeScript config. | 1
|  | 2 | Infra | Init Express/Socket.io repo | Create a separate repo/service for the real-time server. Basic Express boilerplate + TS config. | 1
|  | 3 | Infra | Set up Postgres | Provision a Postgres DB (local or hosted e.g. Neon/Supabase). Get connection string. | 1
|  | 4 | Infra | Install & configure Drizzle | Install Drizzle ORM in both repos where needed, create db/schema folder structure. | 1.5
|  | 5 | Infra | Set up Redis | Provision Redis (local or Upstash). Test connection from both services. | 1
|  | 6 | Infra | Set up Winston logging | Configure a Winston logger in both the Next.js app and the socket server for consistent structured logging. | 1
|  | 7 | Frontend | Install frontend libraries | TanStack Query, Zustand, React Hook Form, Zod, shadcn/ui, next-themes. | 1
|  | 8 | Infra | Set up shared env vars | JWT_SECRET, DATABASE_URL, REDIS_URL shared/consistent across both repos. | 0.5
|  | 9 | Integration | Verify local setup | Confirm both servers run locally and connect successfully to Postgres and Redis. | 1
Day 2 | Auth - Signup Flow (Full-Stack) | 1 | Backend | Define users table | Design users schema in Drizzle (id, name, email, password_hash, role, avatar_url, created_at) and migrate. | 1
|  | 2 | Backend | Password hashing utility | Build hash/compare helper using bcrypt or argon2. | 0.5
|  | 3 | Backend | Build signup route | POST /auth/signup - validate input, hash password, create user, return tokens. | 1.5
|  | 4 | Frontend | Signup page UI | Build the signup form layout using shadcn components. | 1.5
|  | 5 | Frontend | Signup form validation | Wire React Hook Form + Zod schema matching the backend's expected input. | 1
|  | 6 | Frontend | Connect signup to API | Use a TanStack Query mutation to call the signup route; store returned tokens/user in Zustand. | 1.5
|  | 7 | Integration | Test signup end-to-end | Verify the full path: form submit -> API -> DB write -> token stored -> user redirected. | 1
Day 3 | Auth - Login, Session & Auth Pages (Full-Stack) | 1 | Backend | Build login route | POST /auth/login - verify credentials, issue short-lived JWT access token. | 1.5
|  | 2 | Backend | Refresh token + Redis | Implement long-lived refresh token, store/track it in Redis for revocation. | 1.5
|  | 3 | Frontend | Login page UI | Build the login form using shadcn components. | 1.5
|  | 4 | Frontend | Connect login to API | Wire login form (RHF + Zod) to the login route via TanStack Query; store tokens in Zustand. | 1.5
|  | 5 | Frontend | Protected route wrapper | Redirect unauthenticated users; handle silent access-token refresh using the refresh token. | 1.5
|  | 6 | Frontend | Live bid preview + How It Works | Add the animated live-bid-preview component to the auth page (simulated/mock bid loop for now — swapped for the real public feed on Day 12) and build the How It Works page. | 2
|  | 7 | Integration | Test full auth journey | Verify signup -> login -> refresh -> logout -> protected-route access all work together. | 1
Day 4 | Password Reset Flow (Full-Stack) | 1 | Backend | Define verification_tokens table | tokenTypeEnum (password_reset, email_verification, email_change), tokenHash (sha256, never store raw), identifier, metadata (jsonb), expiresAt, usedAt, ip/userAgent. Add indexes on tokenHash and (userId, type). Migrate. | 1.5
|  | 2 | Backend | Token generation utility | Generate a random raw token, return it to send in the email link, store only its sha256 hash + expiry in the DB. | 1
|  | 3 | Backend | POST /auth/forgot-password | Create a password_reset token for the user (if they exist), send an email containing the raw token as a link. Always respond the same way whether or not the email exists (avoid leaking which emails are registered). | 1.5
|  | 4 | Backend | POST /auth/reset-password | Hash the incoming token, look it up, check type/expiresAt/usedAt, update the password, mark the token used, revoke the user's other refresh tokens in Redis. | 1.5
|  | 5 | Frontend | Forgot Password page | Wire the already-designed Forgot Password page to POST /auth/forgot-password. | 1
|  | 6 | Frontend | Check Your Email + Reset + Success pages | Wire the already-designed Check Your Email, Reset Password, and Reset Success pages to their routes. | 1.5
|  | 7 | Integration | Test full reset flow end-to-end | Forgot password -> email link -> reset -> success -> confirm old sessions are revoked and the new password works. | 1
Day 5 | Email Verification & Account Update (Full-Stack) | 1 | Backend | POST /auth/send-verification | Create an email_verification token for the current user (same generation utility as password reset). | 1
|  | 2 | Backend | POST /auth/verify-email | Hash the incoming token, validate type/expiry/usedAt, mark the user's email as verified, mark the token used. | 1
|  | 3 | Backend | Email-change flow | PATCH /account/email creates an email_change token with the new address in metadata; GET /auth/confirm-email-change validates the token and updates users.email. | 1.5
|  | 4 | Frontend | Verify-email prompt | Show a banner/prompt for unverified users with a resend button, wired to send-verification. | 1
|  | 5 | Frontend | Change-email UI in Settings | Add a change-email field in Settings, wired to the email-change flow, with a clear confirmation message. | 1.5
|  | 6 | Integration | Test verification + email-change end-to-end | Signup -> verify email works; change email -> confirmation link -> email actually updates. | 1
Day 6 | Auction & Settings Schema (Backend) | 1 | Backend | Define categories table | Design categories schema (id, name, slug) and seed initial categories. | 1
|  | 2 | Backend | Define auctions table | Design auctions schema incl. seller_id, category_id, status, timestamps. | 1
|  | 3 | Backend | Define auction_settings table | Design settings schema: min_bid_increment, reserve_price, buy_now_price, auto_extend, max_bids_per_user, require_verified_bidder, custom_rules. | 1
|  | 4 | Backend | Run migrations | Migrate and verify categories, auctions, and auction_settings tables exist correctly. | 0.5
|  | 5 | Backend | Note | This day is backend-only by nature — there's no meaningful frontend to build until the create/edit API exists (next day).
Day 7 | Seller Auction CRUD (Full-Stack) | 1 | Backend | Create-auction route | POST /auctions - Zod-validated, creates the auction plus its linked auction_settings row. | 1.5
|  | 2 | Backend | Edit-auction route | PATCH /auctions/:id - update auction fields and settings together. | 1
|  | 3 | Backend | Delete-auction route | DELETE /auctions/:id - remove auction, cascading settings/images. | 0.5
|  | 4 | Frontend | Create-auction form UI | Build the listing form: title, description, category, images, price, and rules/settings fields. | 2
|  | 5 | Frontend | Edit-auction form UI | Reuse the create form pre-filled with existing auction + settings data. | 1
|  | 6 | Frontend | Wire forms to API | Connect create/edit forms via TanStack Query mutations with matching Zod validation. | 1.5
|  | 7 | Integration | Test seller CRUD end-to-end | Verify a seller can create, edit, and delete an auction with rules, reflected correctly in the DB. | 1
Day 8 | Browse & Discovery (Full-Stack) | 1 | Backend | List auctions route | GET /auctions with category filter + pagination support. | 1.5
|  | 2 | Frontend | Browse page layout | Build the grid/list layout and the reusable AuctionCard component (image, price, countdown, category badge). | 2
|  | 3 | Frontend | Fetch & filter wiring | Fetch auctions with TanStack Query; wire category filter UI to URL query params matching the backend filter. | 1.5
|  | 4 | Frontend | Loading/empty states | Add skeleton loaders and empty-state messaging. | 0.5
|  | 5 | Integration | Test browse + filter end-to-end | Verify filtering and pagination work correctly against real seeded data. | 1
Day 9 | Auction Detail Page (Full-Stack) | 1 | Backend | Auction detail route | GET /auctions/:id - includes settings, images, seller info, and current highest bid. | 1
|  | 2 | Frontend | Detail page layout | Build the full auction detail page structure. | 1.5
|  | 3 | Frontend | Countdown timer component | Live-updating countdown to the auction's end time. | 1
|  | 4 | Frontend | Image gallery component | Render auction_images with a gallery/carousel. | 1.5
|  | 5 | Frontend | Display rules & seller info | Show reserve/buy-now/min-increment/custom rules from auction_settings, plus seller info section. | 1
|  | 6 | Integration | Test detail page end-to-end | Verify real data renders correctly from DB through API to UI. | 1
Day 10 | Real-Time Infrastructure (Backend-led, Frontend connects) | 1 | Backend | Socket.io server instance | Attach Socket.io to the Express server. | 1
|  | 2 | Backend | JWT auth on handshake | Verify JWT from socket.handshake.auth.token before allowing a connection. | 1.5
|  | 3 | Backend | Room join/leave logic | Join an auction's room on connect, leave on disconnect. | 1.5
|  | 4 | Backend | Redis client + key structure | Connect Redis; design keys for current highest bid / active bidders per auction. | 1.5
|  | 5 | Frontend | Socket client connection | Connect to the Socket.io server from the auction detail page; join the room on mount, leave on unmount. | 1.5
|  | 6 | Integration | Test connect/join/leave | Verify the frontend and backend agree on connection, auth, and room membership. | 1
Day 11 | Bid Placement (Full-Stack) | 1 | Backend | Place-bid event handler | Socket event that receives a bid attempt. | 1.5
|  | 2 | Backend | Validate bid amount | Check against current highest bid + min_bid_increment from auction_settings. | 1
|  | 3 | Backend | Handle race conditions | Use a Redis lock or atomic check-and-set to prevent double-bidding. | 2
|  | 4 | Backend | Persist bid + update cache | Save valid bid to Postgres via Drizzle; update the Redis highest-bid cache. | 1
|  | 5 | Frontend | Bid input UI | Build the bid amount input + submit button wired to the socket emit. | 1
|  | 6 | Frontend | Handle bid responses | Show success confirmation or inline error (bid too low, auction ended, etc.) matching backend error events. | 1
|  | 7 | Integration | Test valid/invalid bids end-to-end | Confirm both success and every rejection case behave correctly on the frontend. | 1
Day 12 | Live Broadcast & Anti-Sniping (Full-Stack) | 1 | Backend | Broadcast bid update | Emit 'new-highest-bid' to everyone in the auction's room. | 1
|  | 2 | Backend | Auto-extend logic | Extend end_time if a bid lands within the anti-sniping window (if enabled in auction_settings). | 1.5
|  | 3 | Backend | Public activity feed room | Create a separate, unauthenticated public Socket.io room; broadcast a sanitized version of every bid (item name/thumbnail, bid amount, masked bidder name) to it. | 1.5
|  | 4 | Frontend | Real-time UI update | Listen for bid events and update the highest bid/UI instantly, no refresh. | 1.5
|  | 5 | Frontend | Reflect auto-extend in timer | Update the countdown timer live if the backend extends the end time. | 1
|  | 6 | Frontend | Wire auth page live feed | Replace the auth page's simulated/mock bid loop with a real connection to the public activity feed room (no login required). | 1.5
|  | 7 | Integration | Multi-tab concurrent bidding test | Test with multiple browser tabs bidding at once, including near the anti-sniping window; confirm the public feed updates too. | 1.5
Day 13 | User Dashboard - Overview & My Auctions (Full-Stack) | 1 | Backend | Overview stats route | GET /dashboard/overview - active bids, active auctions, and similar summary stats. | 1
|  | 2 | Backend | My-auctions route | GET /dashboard/my-auctions - auctions the user is selling. | 1
|  | 3 | Frontend | Dashboard layout + nav | Build the shared dashboard layout and sidebar navigation. | 1.5
|  | 4 | Frontend | Overview page UI | Build stat cards / summary widgets consuming the overview route. | 1.5
|  | 5 | Frontend | My Auctions page UI | Build the list/table view with status, consuming the my-auctions route. | 1.5
|  | 6 | Integration | Test both pages end-to-end | Verify both pages reflect real, current user data. | 1
Day 14 | User Dashboard - My Bids & Settings (Full-Stack) | 1 | Backend | My-bids route | GET /dashboard/my-bids - auctions the user is bidding on, with current status. | 1
|  | 2 | Backend | Settings route | GET/PATCH /dashboard/settings - profile, password. | 1
|  | 3 | Frontend | My Bids page UI | Build the list showing bid status: winning / outbid / won / lost. | 1.5
|  | 4 | Frontend | Settings page UI | Build the form to edit profile info and change password. | 1.5
|  | 5 | Integration | Test both pages end-to-end | Verify bid status logic and settings updates persist correctly. | 1
Day 15 | Admin Dashboard - Layout & Auctions Monitor (Full-Stack) | 1 | Backend | Admin route protection | Middleware restricting admin routes/pages to role=admin only. | 1
|  | 2 | Backend | Admin auctions route | GET /admin/auctions - all auctions with filters. | 1
|  | 3 | Frontend | Admin layout | Build the shadcn dark sidebar layout for the admin section. | 1.5
|  | 4 | Frontend | Auctions monitoring table | Table UI with status filters and search, consuming the admin auctions route. | 1.5
|  | 5 | Integration | Test admin access + monitoring | Verify non-admins are blocked and the monitoring table reflects real data. | 1
Day 16 | Admin Dashboard - Users & Activity Monitor (Full-Stack) | 1 | Backend | Admin users route | GET /admin/users - list all users with role/activity info. | 1
|  | 2 | Backend | Admin activity route | GET /admin/activity - recent bids, signups, active auction count. | 1.5
|  | 3 | Frontend | Users monitoring table | Table UI for browsing/searching users. | 1.5
|  | 4 | Frontend | Activity dashboard widgets | Charts/cards summarizing platform activity, consuming the activity route. | 1.5
|  | 5 | Integration | Test both admin views | Verify both views reflect real platform data accurately. | 1
Day 17 | Payments - Checkout Flow (Full-Stack) | 1 | Backend | Stripe project setup | Create Stripe account, get API keys, add to env vars. | 0.5
|  | 2 | Backend | Checkout session route | Build a route to create a Stripe Checkout session for the winning bidder. | 1.5
|  | 3 | Backend | Webhook + payments table | Handle payment success/failure events from Stripe; persist to the payments table. | 1.5
|  | 4 | Frontend | Checkout trigger UI | Build the payment/checkout button and flow for the winning bidder. | 1.5
|  | 5 | Integration | Test with Stripe test cards | Verify the full checkout flow using Stripe's test card numbers. | 1
Day 18 | Payments - Auction End & Notifications (Full-Stack) | 1 | Backend | Set up BullMQ | Install BullMQ; create a dedicated ioredis connection for it with maxRetriesPerRequest: null (required by BullMQ), separate from the general-purpose Redis client. | 1
|  | 2 | Backend | Schedule auction-end job | When an auction is created, schedule a BullMQ delayed job to fire exactly at its end_time. | 1.5
|  | 3 | Backend | Auction-end job processor | BullMQ worker: marks the auction ended and determines the winner when the job fires. | 1.5
|  | 4 | Backend | Winner notification | Create a notification record when a user wins an auction. | 1
|  | 5 | Backend | Payment failure handling | Handle failed/retried payments gracefully. | 1
|  | 6 | Frontend | Winner notification UI | Build the winner banner and a notification list/inbox consuming the notifications model. | 1.5
|  | 7 | Integration | Test full flow end-to-end | Auction ends -> BullMQ job fires -> winner notified -> payment completed, verified start to finish. | 1.5
Day 19 | Full Polish Pass (Frontend-led) | 1 | Frontend | Polish auth pages | Visual review and refinement of signup/login/How-It-Works pages. | 1
|  | 2 | Frontend | Polish browse/detail pages | Visual review and refinement of browse and auction detail pages. | 1.5
|  | 3 | Frontend | Polish dashboard pages | Visual review and refinement of all 4 user dashboard pages. | 1.5
|  | 4 | Frontend | Polish admin pages | Visual review and refinement of admin dashboard pages. | 1
|  | 5 | Frontend | Loading/empty/error states | Verify these states are handled and styled consistently app-wide. | 1.5
|  | 6 | Frontend | Consistent theming | Confirm light-mode-first theming and the dark admin sidebar are applied consistently. | 1
Day 20 | Deployment (Full-Stack) | 1 | Frontend | Deploy Next.js app | Deploy the frontend/API app to Vercel. | 1
|  | 2 | Backend | Deploy Socket.io server | Deploy the Express/Socket.io server to Railway/Render/Fly.io. | 1.5
|  | 3 | Backend | Configure prod env vars | Set all required env vars on both deployed platforms. | 1
|  | 4 | Backend | Configure CORS | Set up CORS rules between the deployed frontend and Socket.io server. | 1
|  | 5 | Integration | Test production build locally | Run a production build locally before pushing live. | 1
|  | 6 | Integration | Verify live URLs | Confirm both deployed services are reachable and communicating correctly. | 0.5
Day 21 | Final Testing & Interview Prep | 1 | Integration | Live concurrent bidding test | Test real concurrent bidding on the live deployment. | 1.5
|  | 2 | Integration | Fix last-minute bugs | Address any issues found during live testing. | 2
|  | 3 | Docs | Write architecture notes | Document Socket.io flow, Redis usage, JWT auth, and DB schema for interview prep. | 1.5
|  | 4 | Docs | Prepare demo walkthrough | Write a short script for demoing the app in interviews. | 1
|  | 5 | Docs | Final resume/project alignment check | Make sure resume description matches the finished project accurately. | 0.5